# MUNICIPAL TURNAROUND TEMPLATE – UBUNTU  MUNICIPALITY

| No. | Priority Turn Around Focal Area | January 2010 (Current Situation/ Baseline) | Target for December 2010 (Changed Situation) | Municipal Action | Unblocking Action Needed from other Spheres and Agencies (e.g. intervention or technical support) | Human Resource allocated | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Allocated | Projected |
| 1. | Basic Service Delivery |  |  |  |  |  |  |  |
| 1.1 | Access to water management and maintenance | VICTORIA WEST: Provision of water contract – AM Conroy that is providing about 50% of water | April 2010 | Source a legal opinion – Contract proposed evaluation | Legal opinion from DWA & COGSHTA & DBSA | Municipal Manager & Technical Manager |  |  |
|  |  | Finalization of Water Provision (20 households outstanding) | April 2010 | Project Completion by own work force |  | Technical Manager |  |  |
|  |  | Replacement of old asbestos reticulation pipes (ageing infrastructure @ Richmond & Loxton) | Funding Sourcing | Business Plan | DWA – MIG to look at alternative funding | Technical Manager |  |  |
|  |  | Overconsumption and waste of water (1000 without metres @ Richmond & Loxton) | Review present policy; and Facilitation funds; and Facilitate a procurement process; and Contractor on site by December 2010 | Report back process with all stakeholders; Review policy; & Facilitate procurement process | DWA, DBSA Technical Support – Legal Process | Technical Manager CFO |  |  |
|  |  | Shortage of water bore holes | Bore a sufficient number of bore holes for the municipal water demand | Request the bore hole drilling machine | DWA– Bore hole development team | Technical manager |  |  |
|  |  | RICHMOND: See point 3, 4, 5 & 6 LOXTON: See point 2,3,4,5 & 6 |  |  |  | Technical Manager |  |  |
| 1.2 | Access to sanitation management & maintenance | VICTORIA WEST: Bulk infrastructure on 70 sites not yet in place | To install a sewerage network on the outstanding 70 sites | Install the network | COGTA integrated planning COGHSTA to release funding for 270 houses | Mayor, Municipal Manager & Technical Manager |  |  |
|  |  | LOXTON: All have full water borne systems |  |  |  |  |  |  |
|  |  | RICHMOND: Informal sites about 70 buckets | Town establishment process finalised | Monitor process | COGTA & COGHSTA to finalise this process as a matter of urgency with Dept of Human Settlement |  |  |  |
| 1.3 | Access to electrical management & maintenance |  |  |  | Long term infrastructure planning and funding |  |  |  |
|  |  | LOXTON: 36 households must still be supplied with electricity |  | Liaise with Eskom | DME & SALGA to facilitate the process |  |  |  |
| 1.4 | Refuse Removal, Victoria West, Richmond & Loxton | Upgrading of Land fill sites | Complete the feasibility study | EIA feasibility study Victoria West landfill Sites, planning & managing, cleaning and upgrade of Landfill sites licensing of landfill sites | DWA & Environmental Affairs | Technical Manager |  |  |
| 1.5 | Access and maintenance of municipal roads | Gravel roads in town in need of repair |  | COGHSTA & Dept of Roads & District municipality to discuss to graders by municipalities |  |  |  |  |
| 1.6 | Formalisation of informal settlements | VICTORIA WEST: Bulk infrastructure on 70 sites not yet in place RICHMOND: Informal sites about 70 buckets | To install a sewerage network on the outstanding 70 sites Town establishment process finalised | Install the network Monitor process | COGTA integrated planning COGHSTA to release funding for 270 houses COGTA & COGHSTA to finalise this process as a matter of urgency with Dept of Human Settlement | Mayor, Municipal Manager & Technical Manager |  |  |
| 2. | Public Participation |  |  |  |  |  |  |  |
| 2.1 | Functionality of Ward Committees | All ward committees functional Further training necessary |  | To facilitate ward committee members that are temporary employed in the road maintenance project Facilitate the training process of ward committee members | SALGA & COGHSTA COGHSTA to facilitate the debate surrounding the remuneration of ward committee members | Mayor & Corporate Manager | 70 000 |  |
| 2.2 | Broader public participation policies and plans | Interaction with community not satisfactory | Programme must be adopted by Council of bi-monthly meetings with stakeholders | Develop program for Council meets the people bi-monthly | COGHSTA to facilitate the process of getting sector departments involved in local government issues | Speaker, Municipal Manager & Ward Councillors | 30 000 |  |
| 2.3 | Broader public participation | Only public meetings & notices | Issue a municipal news letter on a bi-monthly basis | To publish a news letter |  | Office of the Mayor & MM | 20 000 |  |
| 2.4 | Complaints management systems | We have a complaints register (system is lacking) | Monthly | To enhance the functionality of the register (Richmond to receive special attention) |  | Manager & Heads of Dept. | 10 000 |  |
| 2.5 | Front Desk Interface | Operational but can be enhanced The offices at Victoria West, Richmond & Loxton not accessible for the disabled | To make the two offices accessible for the disabled | To discuss & plan the proposed alterations to the 3 offices To facilitate the process in making the 2 offices accessible |  | Municipal Manager & Technical Manager | 50 000 |  |
| 2.6 | Appointment of CDW’s vs. number of wards | 4 wards, 7 CDW’s and one vacancy (Richmond) |  |  | COGHSTA to facilitate the debate of the transferring of funds and the authority to appoint CDW’s by municipalities and the development of applicable guidelines in this respect |  | n/a |  |
| 3. | Governance |  |  |  |  |  |  |  |
| 3.1 | Political Management and Oversight |  |  |  |  |  |  |  |
| 3.1.1 | Stability of Councils | Needs better implementation and clarity needs improvement Not fully operational | March 2010 March 2010 March 2010 March 2010 | Council Item Council Item Council Item Council Item |  |  | 10 000 |  |
| 3.1.2 | Delegation of functions between political and administration | Serviced by the District Council No proper oversight |  | Budget for Committee Advertise for services & appointment – headhunting Training on legislation Mayor attending (ELMPD) |  | Mayor & manager SALGA | 80 000 |  |
| 3.1.3 |  |  |  |  |  |  |  |  |
| 3.2 | Administration |  |  |  |  |  |  |  |
| 3.2.1 | Recruitment, Selection and Suspension of employees | No suspensions Two arbitration cases pending Process of recruitment of s57 appointments as well as other appointments underway Recruitment policy in place (no review) | To appoint the Technical Manager & the CFO | To conclude the process of advertising, short listing, interviews & appointments |  |  | 80 000 |  |
| 3.2.2 | Vacancies (Top 4- MM, CFO, Planner, Engineer) | Vacancies- Technical Manager & CFO | Appointment of both | To follow due process as above |  |  | 20 000 |  |
| 3.2.3 | Vacancies in other levels | Functional organogram 57 vacancies | To fill 60% of those posts by 30 June 2010 | To complete the recruitment & appointment process by 30 June 2010 |  | Corporate Manager | 20 000 |  |
| 3.2.4 | Top 4 appointed with signed Performance Agreements | Two appointed both signed Performance agreements |  |  |  |  | 100 000 |  |
| 3.2.5 | IDP adopted by Council | Yes |  |  |  |  | 150 000 |  |
| 3.2.6 | SDBIP adopted by Council | Yes approved by the Mayor |  |  |  |  | 20 000 |  |
| 3.2.7 | Organisational Performance Management System | Only for s57 employees Policy in place |  |  |  |  | Part of 3.2.4 |  |
| 3.2.8 | S 46 report for 2008/09 adopted by Council |  |  |  |  |  | n/a |  |
| 3.2.9 | Mid-year assessment report for 2009/10 adopted by Council | YES |  |  |  |  | n/a |  |
| 3.2.10 | Performance Audit Committee (PAC) appointed | NO |  |  |  |  | 50 000 |  |
| 3.2.11 | PAC report presented to Council | NO |  |  |  |  | n/a |  |
| 3.2.12 | Skills Audit conducted for all employees | YES |  | A new audit will be done |  |  | 100 000 |  |
| 3.2.13 | Skills development for employees | Skills development plan in place |  |  |  |  | 50 000 |  |
| 3.3 | Labour Relations |  |  |  |  |  |  |  |
| 3.3.1 | Functionality of Local Labour Relations | YES (gender equity not yet reached) |  |  |  |  | 30 000 |  |
| 3.3.2 | Functionality of LLF | Functions effectively |  |  |  |  | Part of 3.3.1 |  |
| 4. | Financial Management |  |  |  |  |  |  |  |
| 4.1 | Revenue enhancement |  |  |  |  |  | 300 000 |  |
| 4.2 | Debt management |  |  |  |  |  | 150 000 |  |
| 4.3 | Cash flow management |  |  |  |  |  | 50 000 |  |
| 4.4 | Repairs and maintenance provision |  |  |  |  |  |  |  |
| 4.5 | Capital expenditure |  |  |  |  |  |  |  |
| 4.6 | Clean Audit |  |  |  |  |  | 800 000 |  |
| 4.7 | Submission of Annual Financial Statements |  |  |  |  |  | 50 000 |  |
| 4.8 | MIG expenditure | Under spending | Total spend by 31 March 2010 | Submit latest expenditure report Enhance expenditure Train personnel in MIGMIS for reporting |  |  | 50 000 |  |
| 4.9 | Asset management |  |  |  |  |  | 600 000 |  |
| 4.10 | Credibility and transparency of Supply Chain Management |  |  |  |  |  | 50 000 |  |
| 5. | Local Economic Development |  |  |  |  |  |  |  |
| 5.1 | LED Strategy adopted by Council | NO |  |  | DBSA to assist with process |  | 500 000 |  |
| 5.2 | LED Plan aligned to the PGDS and adopted by Council | NO |  |  |  |  | 100 000 |  |
| 5.3 | LED manager appointed | NO | To be appointed by 31 March 2010 | Appoint the official |  | Corporate Services | 30 000 |  |