## Sheet1
UBUNTU MUNICIPALITY : INTEGRATED DEVELOPMENT PROJECTS | [11 empty] | DATE UPDATED
26/03/2013
PROJECT |  |  | PROJECT DETAILS AND OBJECTIVES |  |  |  | ESTIMATED COST |  |  |  |  | PROJECT TOTAL | SOURCE
No | DESCRIPTON | TERM | QTY | STD | LOCALITY | PROGRESS MADE
[7 empty] | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18
INFRASTRUCTURE
WATER SUPPLY
1 | BULK METER (ZONAL /AREA METERS) |  | 36 | RDP | VW/RM/LOX | 10 INSTALLED |  | 180000 |  |  |  | 180000 | DWAE/MIG
2 | GAS CHLORINATION |  | 7 | RDP | VW/RM | NOT ACHIEVED |  |  |  |  | 1400000 | 1400000 | DWAE/MIG
3 | INSTALL WATERSOFTENERS |  | 7 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 2800000 | 2800000 | DWAE/MIG
4 | REPLACE WATER NETWORK (ASBESTOS PIPES) |  | 3 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 2000000 | 2000000 | DWAE/MIG
5 | BOREHOLE DEVELOPMENT |  | 1 | RDP | VW/RM | NOT ACHIEVED |  |  | 5000000 |  |  | 5000000 | DWAE/MIG
6 | REPLACE WATER NETWORK/METERS |  | DETERM. | RDP | HUT/MER | NOT ACHIEVED |  |  |  |  | 69000000 | 69000000 | DWAE/MIG
7 | PURCHASE WATERMETERS |  | 2000 | RDP | VW/RM/LOX | 500 ACHIEVED |  |  |  |  | 300000 | 300000
8 | SERVICE OF ERVEN |  | 2000 | RDP | VW/RM/LOX | 36 IN PROCESS |  |  | 7000000 |  |  | 7000000
HOUSING (ALL CATEGORIES)
9 | HOUSING & SERVICES |  | 2000 | RDP | VW/RM/LOX | 60 ACHIEVED | 7000000 | 14000000 | 14000000 | 14000000 | 91000000 | 140000000 | DPLG
10 | SURVEY OF SITES |  | 2000 | RDP | VW/RM/LOX | 850 ACHIEVED |  | 400000 |  |  |  | 400000 | DPLG
11 | RECTIFICATION OF OLD SCHEME HOUSES |  | 1500 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 11250000 | 11250000 | DPLG
TRANSPORT, ACCESS ROADS & STREETS
12 | PUBLIC TRANSPORT PLAN |  | DETERM. | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 200000 | 200000 | DEPT TRANSP.
13 | ACCESS ROADS & STREETS |  | 55 KM | DETERM. | VW/RM/LOX | 17 KM ACHIEVED | 15000000 | 13000000 | 13000000 | 13000000 | 15000000 | 69000000 | MIG
SANITATION
14 | REPLACE BUCKETS SYSTEM |  | 350 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  | 2000000 |  |  | 2000000 | MIG
15 | UPGRADING OXIDATION PONDS (AIRATO) |  | 1 | RDP | LOX | ACHIEVED | [5 empty] | 1600000 | MIG
16 | UPGRADING OF SEWER PUMPSTATION |  | 1 | RDP | RM | NOT ACHIEVED |  |  |  |  | 300000 | 300000 | MIG
17 | NEW PUMPSTATION |  | 1 | RDP | VW | NOT ACHIEVED |  |  |  |  | 1000000 | 1000000
18 | SEWER NETWORK |  | 1 | RDP | VW | NOT ACHIEVED |  |  |  |  | 2000000 | 2000000
STORMWATER DRAINAGE
19 | EXTERNAL DRAINAGE |  | DETERM. | RDP | VW/RM/LOX | IN PROCESS |  |  |  |  | 5000000 | 5000000 | MIG
20 | INTERNAL DRAINAGE |  | DETERM. | RDP | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 250000 | 250000 | MIG
21 | DEVELOP A SOLID WASTE SITE FOR V/WEST |  | 1 | RDP | VW/RM/LOX | NOT ACHIEVED | 4675000 |  |  |  |  | 4675000 | MIG
22 | INTERNAL SERVICE UPGRADING (DUST BINS) |  | 2500 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 550000 | 550000 | UBUNTU
25 | UPGRADING OF SOLID WASTE (FEASABILITY STUDY) |  |  |  | LOX/RM | NOT ACHIEVED |  | 3758000 |  |  |  | 3758000
ELECTRICITY
23 | AREA LIGHTING AT TOWNS |  | 4 | RDP | VW/RM/HUT | 8 ACHIEVED | 1600000 |  |  |  |  | 1600000 | MIG
24 | UPGRADING OF HIGH VOLTAGE LINE |  | 10KM | DETERM. | V/WEST | NOT ACHIEVED |  |  |  |  | 40000000 | 40000000 | MIG
25 | UPGRADING OF TELLEMETRY SYSTEM |  | 3 | DETERM. | VW/RM/LOX | ACHIEVED | [5 empty] | 550000 | MIG/DWAE
26 | INSTALL PREPAID METERS/CONNETIONS |  | 1000 | RDP | VW/RM/LOX | NOT ACHIEVED | 220000 | 495000 | 495000 | 495000 | 495000 | 2200000 | UBUNTU/DBSA
27 | STREETLIGHTING |  | 1000 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  | 10000 |  |  | 10000 | MIG
28 | SOLAR GEYSERS |  | 1500 | RDP | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 4500000 | 4500000 | ESKOM
TOTAL ESTIMATED COSTS OF ITEMS CARRIED FORWARD TO PAGE 2 | [6 empty] | 28495000 | 31833000 | 41505000 | 27495000 | 247045000 | 378523000

## Sheet2
UBUNTU MUNICIPALITY : INTEGRATED DEVELOPMENT PROJECTS | [11 empty] | DATE UPDATED
26/03/2013
PROJECT DETAILS AND OBJECTIVES |  |  | PROJECT DETAILS & OBJECTIVES |  |  |  | ESTIMATED COST |  |  |  |  | PROJECT TOTAL | SOURCE
No | DESCRIPTON | TERM | QTY | STD | LOCALITY | PROGRESS MADE
[7 empty] | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18
TOTAL ESTIMATED COSTS C/F FROM PAGE 1 | [6 empty] | 28495000 | 31833000 | 41505000 | 27495000 | 247045000 | 378523000
AGRICULTURAL
29 | UPGRADING OF INFRASTRUCTURE (COMMONAGE) |  | 3 | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  | 2250000 |  |  | 2250000 | DLA
30 | ACQUIRING OF LAND (COMMONAGE) |  |  |  | VW | NOT ACHIEVED |  |  |  | 15000000 |  | 15000000 | DLA
31 | LAND FOR SMALL FARMERS |  | DETERM. | DETERM. | RM | NOT ACHIEVED |  |  |  |  | 4500000 | 4500000 | DLA
32 | LAND CARE PROGRAMME (COMMONAGE) |  |  |  | RM | NOT ACHIEVED |  |  |  |  | 300000 | 300000 | DLA
33 | CASP PROJECT |  |  |  | RM | NOT ACHIEVED |  |  | 1500000 |  |  | 1500000 | DLA
34 | WOOL SPINNING INDUSTRY |  | DETERM. | DETERM. | HUT | NOT ACHIEVED |  |  |  |  | 15000000 | 15000000 | DLA
COMMUNITY SERVICES
35 | EXTENSION TO CEMETRIES |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  | 3500000 |  |  | 3500000 | COGHSTA
36 | UPGRADING OF SPORTS FACILITIES |  | 3 | DETERM. | VW/RM/LOX | PARTLY ACHIEVED |  |  |  |  | 4000000 | 4000000 | DSAC
37 | TRAINING AND CAPACITY BUILDING OF COMMUNITIES |  | DETERM. | DETERM. | UBUNTU | NOT ACHIEVED |  |  |  | 400000 |  | 400000 | UBUNTU
38 | UPGRADING OF COMMUNITY HALLS |  | 3 | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  | 2000000 |  |  | 2000000 | COGHSTA
39 | WEIGHING BRIDGE |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 3000000 | 3000000 | DTRP
40 | TRAFFIC DEPT FOR DRIVERS LICENCES |  | 1 | DETERM. | RM | IN PROCESS |  | 2680000 |  |  |  | 2680000 | DTRP
41 | PURCHASE OF CHAIRS & TABLES FOR COMMUNITY HALLS |  | 3 | DETERM. | VW/RM/LOX | PARTLY ACHIEVED |  |  |  | 80000 |  | 80000 | UBUNTU
42 | PLAYGROUNDS & PARKS |  | 3 | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  | 550000 |  |  | 550000 | UBUNTU
INSTITUTIONAL
43 | UPGRADING OF MUNICIPAL BUILDINGS |  |  |  | VW/RM/LOX | PARTLY ACHIEVED |  |  |  |  | 400000 | 400000 | UBUNTU
44 | PURCHASE OF FIRE FIGHTING EQUIPMENT |  | 5 | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  |  | 1000000 |  | 1000000 | PKDM
45 | LAND USE MAPS |  | 5 | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 400000 | 400000 | COGHSTA
46 | PURCHASE OFFICE FURNITURE & EQUIPMENT |  | 4 | DETERM. | VW/RM/LOX | PARTLY ACHIEVED |  |  |  |  | 100000 | 100000 | UBUNTU
47 | PURCHASE OF MECHANICAL EQUIPMENT |  | DETERM. | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  |  | 40000 |  | 40000 | UBUNTU
48 | PURCHASE OF ELECTRICAL EQUIPMENT |  | DETERM. | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  | 40000 |  |  | 40000 | UBUNTU
49 | PURCHASE OF EQUIPMENT FOR COMMUNITY HALLS |  | DETERM. | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  | 50000 |  |  | 50000 | UBUNTU
50 | COMPUTERS FOR OFFICES |  | 10 | DETERM. | VW/RM/LOX | PARTLY ACHIEVED |  |  |  | 100000 |  | 100000 | UBUNTU
51 | PURCHASE OF AIRCONDITIONERS & TELEVISION SENDERS |  | DETERM. | DETERM. | VW/RM/LOX | PARTLY ACHIEVED |  |  |  | 20000 |  | 20000 | UBUNTU
52 | BRANDING OF MUNICIPALITY |  |  |  | VW/RM/LOX | PARTLY ACHIEVED |  |  |  |  | 2850000 | 2850000 | UBUNTU
DEVELOPMENT FRAMEWORK
53 | INVESTIGATE THE ECONOMIC DEVELOPMENT POTENTIAL |  | DETERM. | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 500000 | 500000 | UBUNTU
54 | ENVIRONMENTAL MANAGEMENT PLAN |  | DETERM. | DETERM. | VW/RM/LOX | NOT ACHIEVED |  |  |  |  | 300000 | 300000 | UBUNTU
55 | TOURISM & BUSINESS
56 | RESEARCH STEAM SAFARI |  | DETERM. | DETERM. | RM | NOT ACHIEVED |  |  |  |  | 1000000 | 1000000 | DEAT
57 | UPGRADING OF MUSEUM |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 450000 | 450000 | DSAC
58 | HIKING TRAILS |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 400000 | 400000 | DEAT
59 | ESTABLISHMENT OF TOURIST ROUTES |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 1400000 | 1400000 | DEAT
60 | LOXTON CONSERVANCY PROJECT |  | 1 | DETERM. | LX | NOT ACHIEVED |  |  |  |  | 15000000 | 15000000 | DEAT
61 | ERECTING A WASTE MANAGEMENT RECYCLING PROJECT |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 19000000 | 19000000 | DEAT
62 | ERECTING A PARKS AND ACCOMMODATIONS PROJECT |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 15000000 | 15000000 | DEAT
63 | TOILET PAPER MANUFACTURING |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 2400000 | 2400000 | COGHSTA
64 | DEVELOPING OF A LED STRATEGY |  | 1 | DETERM. | VW | NOT ACHIEVED |  |  |  |  | 400000 | 400000 | DEAT
65 | SHOE FACTORY |  | 1 | DETERM. | LX | NOT ACHIEVED |  |  |  |  | 3000000 | 3000000 | DEAT
66 | SCHANSKRAAL SPORT ESTATE DEVELOPMENT |  |  |  |  | NOT ACHIEVED |  |  |  |  | 15000000 | 15000000 | PRIVATE
67 | ENERGY: WIND-FARMING |  |  | DETERM. | V/WEST | NOT ACHIEVED
GRAND TOTALS | [6 empty] | 28495000 | 34513000 | 51395000 | 44135000 | 351445000 | 512133000